## Definitions
Risk Register — Definitions
Likelihood Levels
Level | Score | Description
Almost Certain | 5 | Expected to occur in most circumstances; has happened repeatedly in similar contexts.
Likely | 4 | Will probably occur; strong evidence or history of occurrence.
Possible | 3 | Could occur at some point; some evidence or precedent exists.
Unlikely | 2 | Not expected, but could occur under unusual circumstances.
Rare | 1 | May only occur in exceptional circumstances; very low probability.
Consequence Levels
Level | Score | Description
Catastrophic | 5 | Complete project failure, serious injury, or total loss of key deliverable.
Major | 4 | Significant impact on project objectives, timeline, or safety; major rework required.
Moderate | 3 | Noticeable impact; some rework, delay, or reduced quality, but recoverable.
Minor | 2 | Small impact easily addressed with minimal effort or cost.
Insignificant | 1 | Negligible impact; no meaningful effect on project outcomes.
Risk Score Calculation
Risk Score = Likelihood Score + Consequence Score
Risk Levels
Risk Level | Score Range | Interpretation
Low | 2 – 4 | Acceptable risk; manage through routine procedures.
Moderate | 5 – 6 | Monitor closely; implement mitigation measures where practical.
Significant | 7 | Requires active management and a documented mitigation plan.
High | 8 – 9 | Unacceptable without immediate mitigation; escalate to project lead.
Extreme | 10 | Critical risk; stop activity until risk is reduced or eliminated.
Key Terms
Term |  | Definition
Risk | An uncertain event or condition that, if it occurs, could have a positive or negative effect on one or more project objectives.
Likelihood | The probability of the risk event occurring, rated on a 5-point scale from Rare (1) to Almost Certain (5).
Consequence | The severity of impact if the risk event occurs, rated on a 5-point scale from Insignificant (1) to Catastrophic (5).
Risk Score | A numerical value calculated by adding the Likelihood score and the Consequence score (range: 2–10).
Risk Level | A qualitative classification (Low to Extreme) derived from the Risk Score.
Mitigation Measures | Actions planned or taken to reduce the likelihood or consequence of a risk.
Residual Risk | The remaining level of risk after mitigation measures have been applied.
Risk Area | The category to which the risk belongs (e.g., Mechanical, Electrical, Safety/WHS, Project Management).

## Risk Register
|  |  |  | Columns F, H, I, J auto populates |  |  |  |  | Be detailed in measures. Most areas will have 3 to 5 mitigations required. |  | Columns M,O,P, Q auto populates
Risk ID | Risk Area | Risk Description | Likelihood (Select from pull down) | Score | Consequence (Select from pull down) | Score | Risk Score | Level of Risk | Mitigation measures | RESIDUAL Likelihood (Select from pull down) | Score | RESIDUAL Consequence (Select from pull down) | Score | Risk Score | RESIDUAL Level of Risk
1 | Technology | The OpenAI Gemini API could become unavailable or rate-limited during the final proof-of-concept demonstration, making the AI feedback feature non-functional at the most critical point of the project. | Unlikely | 2 | Major | 4 | 6 | Moderate | Pre-record AI-generated feedback responses as a demonstration backup. Build automatic retry logic into the backend to handle temporary API failures. Verify API availability and quota limits a few days before the demonstration. Store fallback static responses in the application for offline use during the demonstration. | Rare | 1 | Minor | 2 | 3 | Low
2 | Project Management | A team member may become unavailable mid-project due to illness, personal circumstances, or competing academic workloads, causing delays to their assigned development deliverables. | Possible | 3 | Major | 4 | 7 | Significant | Document all work in a shared Google Drive folder from the start of the project so any member can continue where another left off. Cross-train each member on at least one task outside their primary role early in the project. Review task progress at every team standup and redistribute work if a member falls behind. Escalate to the Team Leader immediately if any member is unavailable for more than three consecutive days. | Unlikely | 2 | Minor | 2 | 4 | Low
3 |  | Unexpected spikes in API or cloud hosting usage could push the project's operational costs above the AUD $100 budget ceiling, making it impossible to continue running the platform prototype. | Unlikely | 2 | Moderate | 3 | 5 | Moderate | Set automated billing alerts at AUD $50 and AUD $80 in all cloud platform dashboards. Monitor API token usage and cloud resource consumption regularly. Maintain free-tier hosting plans throughout the prototype phase. Restrict API testing to the development environment only — never run load tests against the paid API endpoint. | Rare | 1 | Minor | 2 | 3 | Low
4 |  | A critical security vulnerability could be found during security testing close to the submission deadline, leaving insufficient time to remediate it and meet the project's core cybersecurity objective. | Unlikely | 2 | Major | 4 | 6 | Moderate | Run the first automated security scan earlier in the project timeline rather than waiting until the final testing phase. Conduct a peer code security review at the end of each development sprint. Address all critical and high severity findings within the same sprint they are discovered. Maintain a security issue backlog and prioritise security fixes above new feature development. | Rare | 1 | Moderate | 3 | 4 | Low
5 |  | The PostgreSQL database storing student quiz results, performance records, and account credentials could become corrupted or accidentally deleted during development, causing permanent loss of all student data and making the analytics dashboard non-functional. | Unlikely | 2 | Major | 4 | 6 | Moderate | Configure automated daily database backups from the start of development. Never run destructive database operations without first confirming a complete backup is in place. Use separate development and production database instances to prevent accidental data loss. Document and version-control all database schema migration scripts. | Rare | 1 | Minor | 2 | 3 | Low
6 |  | The AI system could produce feedback that is inaccurate, misleading, or culturally biased — particularly for students from non-English-speaking backgrounds — causing students to learn incorrect concepts and creating reputational risk for Bottot Pty Ltd. | Possible | 3 | Moderate | 3 | 6 | Moderate | Implement a content moderation function in the backend to screen all AI responses before display. Manually review all AI-generated responses during user acceptance testing. Display a visible AI-generated content disclaimer on the Quiz Page to inform students that feedback may require verification. Establish a student feedback flagging mechanism so users can report incorrect responses. | Unlikely | 2 | Minor | 2 | 4 | Low
3 | Safety/ WHS | Exposed electrical components contact water or a user at an outdoor event, resulting in electric shock or system damage. | Unlikely | 2 | Major | 4 | 6 | Moderate | Conduct a WHS inspection of the unit before each public event. Ensure all team members complete the required workshop safety induction. Label all electrical hazard areas with appropriate warning signage. | Rare | 1 | Moderate | 3 | 4 | Low
|  | Improper battery selection, storage, or charging practice may create risks of short circuit, overheating, or non-compliance with school battery management requirements. | Unlikely | 2 | Major | 4 | 6 | Moderate | Use a sealed off-the-shelf battery or a battery with built-in protection where possible. Follow the school battery management protocol for purchasing, storage, and charging. Ensure battery terminals are protected and that charging arrangements are reviewed before use. | Rare | 1 | Moderate | 3 | 4 | Low
4 | Project Management | Team members are unable to complete assigned tasks on schedule due to competing academic workloads, resulting in delayed audit submissions. | Possible | 3 | Major | 4 | 7 | Significant | Set internal task deadlines one week ahead of each audit submission. Review the project schedule and risk register at every weekly meeting. Distribute tasks equitably based on each team member's availability. | Unlikely | 2 | Minor | 2 | 4 | Low
|  | Purchased components may not meet final design requirements, resulting in return or replacement delays, additional cost, and postponed prototype integration. | Unlikely | 2 | Major | 4 | 6 | Moderate | Review datasheets and interface requirements before purchase. Compare alternative suppliers and candidate components for major items. Prioritise off-the-shelf components with clearly stated specifications and dimensions. | Rare | 1 | Major | 4 | 5 | Moderate
5
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
DO NOT COMPLETE MORE THAN 50 ROWS

## Risk Matrix
Risk Assessment Matrix
Risk Score = Likelihood + Consequence
CONSEQUENCE
|  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
LIKELIHOOD | Almost Certain (5) | 6 Moderate | 7 Significant | 8 High | 9 High | 10 Extreme
| Likely (4) | 5 Moderate | 6 Moderate | 7 Significant | 8 High | 9 High
| Possible (3) | 4 Low | 5 Moderate | 6 Moderate | 7 Significant | 8 High
| Unlikely (2) | 3 Low | 4 Low | 5 Moderate | 6 Moderate | 7 Significant
| Rare (1) | 2 Low | 3 Low | 4 Low | 5 Moderate | 6 Moderate
Risk Level Legend
Low | Score: 2 – 4
Moderate | Score: 5 – 6
Significant | Score: 7
High | Score: 8 – 9
Extreme | Score: 10